# PROJECT TIMELINE AND RESEARCH EXCHANGE PLAN

Hybridizing Metaheuristics with Generative AI Techniques for Selected Graph Problems

Bilateral research cooperation: Bosnia and Herzegovina – Austria  |  2027–2028

# 1. Project implementation schedule

The schedule below is a proposed quarterly implementation plan derived from the five work packages and scientific objectives in the project proposal.

| ID | Activity / work package | 27 Q1 | Q2 | Q3 | Q4 | 28 Q1 | Q2 | Q3 | Q4 | Lead / contribution |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP1 | CMSA–LNS framework and baselines | ● | ● | ● | ● | ● | ● |  |  | Joint |
| WP2 | Generative models for optimization |  |  | ● | ● | ● | ● | ● |  | Austria / joint |
| WP3 | LLM-based heuristic synthesis |  |  | ● | ● |  |  |  |  | Joint |
| WP4 | MCS: models and experiments |  | ● | ● | ● | ● |  |  |  | BiH |
| WP5 | DynEADARP: static and dynamic cases |  |  |  | ● | ● | ● | ● |  | Austria |
| EVAL | Evaluation and generalization |  |  | ● | ● | ● | ● | ● | ● | Joint |
| OUT | Publications and dissemination |  |  |  | ● |  |  |  | ● | Joint |

● = indicative period of active work.

# 2. Milestones and deliverables

| Target period | Milestone | Proposed result |
| --- | --- | --- |
| 2027 Q1–Q2 | M1 | Common experimental interfaces, initial CMSA/LNS baselines, benchmark and instance plan. |
| 2027 Q3–Q4 | M2 | Initial generative destroy-set / candidate-generation prototypes; first comparative experiments. |
| 2027 Q4 | M3 | First consolidated experimental results and draft joint scientific contribution. |
| 2028 Q1–Q2 | M4 | Integrated hybrid variants, LLM-assisted operator study, MCS and DynEADARP evaluations. |
| 2028 Q3 | M5 | Cross-problem generalization, ablation and computational-cost analysis; draft publications. |
| 2028 Q4 | M6 | Final results, documented software components, joint dissemination and project closure. |

The proposal targets at least two joint journal/conference papers.

# 3. Research exchange schedule

The following table presents the participant-specific day allocations.

| Year | Direction | Researcher | Person-days |
| --- | --- | --- | --- |
| 2027 | Austria → BiH | M. Wustinger | 5 |
| 2027 | Austria → BiH | G. Raidl | 5 |
| 2027 | BiH → Austria | M. Đukanović | 3 |
| 2027 | BiH → Austria | T. Zec | 3 |
| 2027 | BiH → Austria | B. Nikolić | 3 |
| 2027 | BiH → Austria | M. Predojević | 3 |
| 2028 | Austria → BiH | M. Wustinger | 10 |
| 2028 | Austria → BiH | G. Raidl | 5 |
| 2028 | BiH → Austria | M. Đukanović | 5 |
| 2028 | BiH → Austria | M. Predojević | 5 |

Total planned mobility: 2027 – 22 person-days (10 Austria → BiH; 12 BiH → Austria); 2028 – 25 person-days (15 Austria → BiH; 10 BiH → Austria).

Grand total: 47 person-days.

# 4. Indicative sequencing of mobility and joint work

- 2027, early phase: Austrian researchers visit BiH to align research objectives, implementation interfaces, datasets and division of responsibilities.

- 2027, middle or late phase: BiH researchers visit Austria for integration work, computational experiments and research coordination.

- 2028, first phase: Austrian partner visits BiH for review of progress, further algorithm development and experimental planning.

- 2028, later phase: BiH team visits Austria to present results and finalize joint contributions.

- 2028, year-end (stated in exchange plan): presenting final results and concluding activities (online).

# 5. Points requiring confirmation

The 2027 BiH → Austria narrative says four researchers will visit for five working days, whereas the individual allocations list three days per person. This document uses the individual allocations (3 × 4 = 12 person-days) pending confirmation. In 2028, two Austria → BiH visits are described, but the allocations are 10 days for M. Wustinger and 5 days for G. Raidl; the exact assignment of researchers to each visit is not specified. Also, the exchange plan includes M. Predojević, who is not among the six researchers listed in the previously supplied project-task document. The team roster should be reconciled before submission.